## Risk Register
PROJECT RISK REGISTER TEMPALTE
|  | Enter Risk Category titles on the Dropdown Key tab to populate the Risk Register Dropdown Menu. |  |  |  | DO NOT ALTER SCORE CELLS Outcomes populate automatically.
REF ID | DATE RAISED | RISK CATEGORY | RISK DESCRIPTION (INCLUDING IF / THEN STATEMENT) | PROBABILITY 1 – 5 | IMPACT 1 – 16 | RISK SEVERITY SCORE Prob x Impact | LIKELY TIMING OF RISK | RISK TRIGGER | MITIGATION / RESPONSE PLAN | STATUS OF MITIGATION / RESPONSE | OWNER | OTHER NOTES
R001 | 16/05/2026 | Website Development | In case the Products page is not created properly, there will be one page missing from the final site. | 3 | 8 | 24 | Iteration 3 | Products page not uploaded or incomplete | Complete the Products page as soon as possible, verify its structure, and have the other team members look at it before merging. | Products page is being completed and reviewed. | Nitin, CEO / project sponsor | Assigned to Iteration 3.
R002 | 18/05/2026 | GitHub / Integration | In case many group members upload updates at once, there may arise GitHub merge conflicts. | 3 | 8 | 24 | During file merge | Conflict message appears in GitHub | Talk to each other before committing changes, fetch the latest version first, and sort out any problems as a team. | The group will review the documents before merging. | Mathias, developer | Watch for GitHub merge conflicts.
R003 | 19/05/2026 | Navigation | In case the page links are incorrect, users may not navigate from Home, Products, and Orders pages. | 3 | 4 | 12 | After upload | Navigation links do not open correct pages | Test the navigation links after uploading all the files and rename files or correct links if necessary. | The navigation links will be reviewed. | Mathias, developer | Check Home, Products, and Orders links.
R004 | 19/05/2026 | GitHub Pages | If the GitHub Pages is not published correctly then the final website link may not work for submission. | 1 | 8 | 8 | Final publishing stage | GitHub Pages shows 404 error or blank page | Review GitHub Pages configuration, ensure the right branch is chosen, and validate the active link through the browser. | GitHub pages will be reviewed. | Mathias, developer | Test the live website link.
R005 | 20/05/2026 | Design / Layout | If the layout of the products page isn’t clear, then the users can experience difficulty viewing product details. | 3 | 4 | 12 | Testing stage | Product cards appear messy or hard to read | Utilize an uncomplicated design with distinct product sections, titles, buttons, and even spacing. | Layouts will remain simple and straightforward. | Olivia Cherry, UX designer | Check spacing and readability.
R006 | 21/05/2026 | File Management | If the file naming is inconsistent, then there will be problems with linking pages on GitHub pages. | 3 | 4 | 12 | After merge | Links work locally but not on GitHub Pages | Employ consistent file naming conventions like Home.html, Products.html, and Orders.html, and utilize the same names for all your links. | File names will be reviewed. | Mathias, developer | Names must match exactly.
R007 | 22/05/2026 | Testing | If the user testing process is not performed properly, then errors will persist after the final submission. | 3 | 8 | 24 | Before final handover | Broken links or layout problems are found late | Undertake manual user acceptance testing and document test results, outcomes, and any action taken. | User testing will be carried out. | Mathias, developer | Record test results and fixes.
R008 | 22/05/2026 | Group Work | If team members fail to complete the assigned pages within time limits, then the process of integration will be delayed. | 3 | 8 | 24 | End of Iteration 3 | Missing files or incomplete tasks | Manage progress on the GitHub board, share updates during meetings, and alert team members to deadlines. | Group work will be monitored. | MD Ilful Hossain, project manager | Track tasks before deadline.
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Dropdown Keys – DO NOT DELETE –
PROJECT RISK REGISTER – MATRIX
PROBABILITY ¦ 1 – 5 | IMPACT ¦ 1 – 16 | PI SCORES ¦ 1 – 80 |  | 1 | 2 | 3 | 4 | 5
1 - RARE | 1 - INSIGNIFICANT | 1 – 2 • NEGLIGIBLE | 1 | 1 | 2 | 3 | 4 | 5
2 - UNLIKELY | 2 - MINOR | 3 – 8 • LOW | 2 | 2 | 4 | 6 | 8 | 10
3 - POSSIBLE | 4 - MODERATE | 10 – 16 • MEDIUM | 4 | 4 | 8 | 12 | 16 | 20
4 - LIKELY | 8 - MAJOR | 20 – 32 • HIGH | 8 | 8 | 16 | 24 | 32 | 40
5 - ALMOST CERTAIN | 16 - SEVERE | 40 – 80 • EXTREME | 16 | 16 | 32 | 48 | 64 | 80
PROBABILITY KEY | IMPACT KEY
1 | 1
2 | 2
3 | 4
4 | 8
5 | 16
Enter Risk Category titles below to populate the Risk Register Dropdown Menu.
RISK CATEGORY
Website Development
GitHub / Integration
Navigation
GitHub Pages
Design / Layout
File Management
Testing
Group Work
Category Nine
Category Ten
PROBABILITY
IMPACT