Note:

1. Please make sure you complete this Report related to each meeting for your Practical Project – Iteration 1 below.

2. Once completed, convert this content to readme.md (GitHub).

# Practical Project - Iteration 2

# Group Meeting Report

| # Notice of Meeting and Agenda | ### Date ### Time ### Location |
| --- | --- |

| ## Sponsor: | John Jamieson | ## Name of Group: | Piccolo |
| --- | --- | --- | --- |
| ## Group Lead: | Olivia Cherry | ## Note taker: | Nitin |
| Attendees: | Olivia Cherry, Mathias Charles Hansen, Nitin Nitin and MD IIful Hossain. |  |  |
| Absent: | None |  |  |
| Please bring: | Laptop |  |  |
| Agenda items: | - Assign Iteration 2 tasks and responsibilities - Progress on Gantt chart - Stakeholder register updates based on Gantt chart - Resource requirement list and GitHub updates |  |  |

# Minutes

| ## Agenda Item 1: | Assign Iteration 2 task and responsibilities | ## Presenter: | Olivia Cherry |
| --- | --- | --- | --- |

#### Discussion:

The group discussed the required tasks for iteration 2, including meeting reports, Gantt chart creation, stakeholder register updates, resource requirements and testing the GitHub repository. Tasks were divided among group members. Olivia took responsibly for meeting reports, Mathias for the Gantt chart, Nitin for assigning task based on the Gantt chart and MD IIful Hossain for the resource requirement list. The group also discussed that some tasks depended on others being completed first.

#### Conclusions:

All tasks have been assigned and dependencies between tasks were identified.

| ## Action items | ## Person responsible | ## Deadline |
| --- | --- | --- |
| Complete meeting reports | Olivia Cherry | Ongoing |
| Begin Gantt chert | Mathias | 2 April |
| Assign task from Gantt chart | Nitin | After Gantt completion |
| Start resource requirement list | MD IIful Hossain | 5 April |

| ## Agenda Item 2: | Progress on Gantt chart | ## Presenter: | Mathias Charles Hansen |
| --- | --- | --- | --- |

#### Discussion:

Mathias began working on the Gantt chart but mentioned difficulty due to limited time and needing more guidance from class materials. The group discussed possible tasks to include so the chart is not empty. Olivia offered to help complete and improve the Gantt chart. A draft version was later uploaded to GitHub as a starting point.

#### Conclusions:

The Gantt chart has been started but needs further detail and refinement.

| ## Action items | ## Person responsible | ## Deadline |
| --- | --- | --- |
| Improve and complete Gantt chart | Mathias and Olivia | 4 April |
| Add more detailed tasks | Mathias | 4 April |
| Review Gantt chart | All members | 5 April |

| ## Agenda Item 3: | Stakeholder register updates based on Gantt chart | ## Presenter: | Nitin |
| --- | --- | --- | --- |

#### Discussion:

The group discussed updating the stakeholder register based on the tasks identified in the Gantt chart. It was noted that this task depends on the Gantt chart being completed first. Nitin later updated the stakeholder register and shared it with the group for feedback.

#### Conclusions:

Stakeholder register has been updated but may need further review and changes.

| ## Action items | ## Person responsible | ## Deadline |
| --- | --- | --- |
| Review updated stake holder register | All members | 15 April |
| Suggest improvements or changes | All members | 15 April |
| Finalise stakeholder register | Nitin | 16 April |

| ## Agenda Item 4: | Resource requirement list and GitHub updates | ## Presenter: | MD IIful Hossain |
| --- | --- | --- | --- |

#### Discussion:

The group discussed creating a resource requirement list, including tools such as GitHub and communication platforms. It was also discussed that the GitHub repository should be regularly updated and tested to ensure all files are correct. Olivia offered to help update the README and support others with GitHub if needed.

#### Conclusions:

Resources need to be documented and GitHub must be kept updated and reviewed.

| ## Action items | ## Person responsible | ## Deadline |
| --- | --- | --- |
| Create resource requirement list | MD IIful Hossain | 16 Aprill |
| Update README and repository | Olivia Cherry | Ongoing |
| Test files and fix issues | All members | Ongoing |

# Other Information

#### Resources:

GitHub repository, Discord group chat and course materials.

#### Date of next meeting:

To be confirmed.